## Summary
Job No: |  | LE21M387 |  |  | Job Description: |  |  | BF-5 for JVML Balllari
Original Contract Value: |  | 964.81 |  |  | Revised Contract Value: |  |  | 964.81 |  |  | Client: |  |  | JSW
Planned Start Date: |  | 2021-04-01 |  |  | Actual Start Date: |  |  | 2021-04-01 |  |  | Running Month: |  |  | 5 |  | Project Type: |  |  | IR
Contr. Completion Date: |  | 2023-07-31 |  |  | Expected Completion Date: |  |  | 2023-07-31 |  |  | ACE GM: |  |  | 106.15 |  | ACE GM %: |  |  | 11%
Planned Duration (Month): |  | 28 |  |  | Expected Duration (Month): |  |  | 28 |  |  | JCR GM: |  |  | 106.1512 |  | JCR GM %: |  |  | 11%
% Completion of Invoice |  | 2.253% |  |  | % Completion of Sales |  |  | 5.117% |  |  | % Completion of Time |  |  | 17.86% |  | Review Month |  |  | 2021-09-01
(All figures are in INR Crs.)
Particulars | TOTAL | ACT till FY21 | For Q1 |  |  | For Q2 |  |  | FTM: Jul+Aug | For Q3 |  |  | For Q4 |  |  | YTD-21-22 |  |  | BAL
|  |  | BUD | TAR | ACT | BUD | TAR | EXP | ACT | BUD | TAR | EXP | BUD | TAR | EXP | BUD | TAR | EXP
SUPPLY
Invoice | 156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.2165 | 23.4625 | 22.9625 | 70.9506 | 70.3875 | 68.8875 | 98.1671 | 93.85 | 91.85 | 64.15
Sales | 156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.12 | 26.12 | 21.25 | 69.3948 | 69.3948 | 63.75 | 95.5148 | 95.5148 | 85 | 71
Cost | 133.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.12 | 26.12 | 21.25 | 69.3948 | 69.3948 | 63.75 | 95.5148 | 95.5148 | 85 | 48.1
SITE SERVICES
Invoice | 808.8121 | 0 | 16 | 16 | 16 | 33.9802 | 33.9802 | 26.9605 | 5.7337 | 85.3208 | 89.0748 | 97.0499 | 143.3697 | 143.9328 | 182.2307 | 278.6707 | 282.9878 | 322.2411 | 486.5709
Sales | 808.8121 | 0 | 25.61 | 25.61 | 25.61 | 57.3234 | 57.3234 | 56.5287 | 23.7592 | 63.25 | 63.25 | 79.7358 | 92.864 | 92.864 | 139.5016 | 239.0474 | 239.0474 | 301.3761 | 507.4359
Cost | 725.5588 | 0 | 25.61 | 25.61 | 25.61 | 57.3234 | 57.3234 | 56.5362 | 23.7667 | 62.7243 | 62.7243 | 80.1231 | 69.9697 | 69.9697 | 105.8082 | 215.6274 | 215.6274 | 268.0774 | 457.4814
TOTAL
Invoice | 964.8121 | 0 | 16 | 16 | 16 | 33.9802 | 33.9802 | 26.9605 | 5.7337 | 112.5373 | 112.5373 | 120.0124 | 214.3203 | 214.3203 | 251.1182 | 376.8378 | 376.8378 | 414.0911 | 550.7209
Sales | 964.8121 | 0 | 25.61 | 25.61 | 25.61 | 57.3234 | 57.3234 | 56.5287 | 23.7592 | 89.37 | 89.37 | 100.9858 | 162.2589 | 162.2589 | 203.2516 | 334.5623 | 334.5623 | 386.3761 | 578.4359
Cost | 858.6588 | 0 | 25.61 | 25.61 | 25.61 | 57.3234 | 57.3234 | 56.5362 | 23.7667 | 88.8443 | 88.8443 | 101.3731 | 139.3646 | 139.3646 | 169.5582 | 311.1423 | 311.1423 | 353.0774 | 505.5814
GM | 106.1532 | 0 | 0 | 0 | 0 | 0 | 0 | -0.007477 | -0.007477 | 0.52571 | 0.52571 | -0.38726 | 22.8943 | 22.8943 | 33.6934 | 23.42 | 23.42 | 33.2987 | 72.8545
GM% as per JCR | 11%

## Q2-Site Services
Details of Q2 - Quantities and Financials (Site Services) | [12 empty] | (All figures are in INR Crs.)
Particulars | UOM | TOTAL | ACT till FY21 | YTD Q1 |  |  | 2021-07-01 |  |  | 2021-08-01 |  |  | 2021-09-01 |  |  | For the Quarter-Q2 |  |  | YTD-Q2
|  |  |  | BUD | TAR | ACT | BUD | TAR | ACT | BUD | TAR | ACT | BUD | TAR | EXP | BUD | TAR | EXP | BUD | TAR | EXP
SITE SERVICES - CIVIL (Quantities)
Excavation | Cum | 305000 |  | 2021-07-01 ACT: 2990; 2021-08-01 ACT: 7920; 2021-09-01 EXP: 10740; For the Quarter-Q2 BUD: 0; For the Quarter-Q2 TAR: 0; For the Quarter-Q2 EXP: 21650; YTD-Q2 BUD: 0; YTD-Q2 TAR: 0; YTD-Q2 EXP: 21650
Concrete | Cum | 132500 |  |  |  |  | 862 | 862 | 545 | 11050 | 11050 | 11101 | 6268 | 6268 | 7368 | 18180 | 18180 | 19014 | 18180 | 18180 | 19014
Shuttering | Sqm | 448500 |  |  |  |  | 431 | 431 | 272.5 | 5525 | 5525 | 5550.5 | 3134 | 3134 | 3684 | 9090 | 9090 | 9507 | 9090 | 9090 | 9507
Rebar | MT | 12840 |  |  |  |  | 586 | 586 | 555 | 605 | 605 | 610 | 626.8 | 626.8 | 737 | 1817.8 | 1817.8 | 1902 | 1817.8 | 1817.8 | 1902
…
SITE SERVICES - CIVIL (Financials)
Invoice | Crs. | 265.9868 |  | 16 | 16 | 16 | 0.97024 | 0.97024 | 0.87187 | 3.6906 | 3.6906 | 3.4561 | 2.4526 | 2.4526 | 3.9325 | 7.1135 | 7.1135 | 8.2605 | 23.1135 | 23.1135 | 24.2605
Sales | Crs. | 265.9868 |  | 0.6 | 0.6 | 0.6 | 0.4677 | 0.4677 | 0.41379 | 1.5751 | 1.5751 | 1.5838 | 1.075 | 1.075 | 1.2637 | 3.1177 | 3.1177 | 3.2613 | 3.7177 | 3.7177 | 3.8613
Cost | Crs. | 197.1717 |  | 0.6 | 0.6 | 0.6 | 0.4677 | 0.4677 | 0.44668 | 1.5751 | 1.5751 | 1.6709 | 1.075 | 1.075 | 1.3819 | 3.1177 | 3.1177 | 3.4994 | 3.7177 | 3.7177 | 4.0994
SITE SERVICES - Mech & Other Items (Quantities)
Raw Steel (Site) | MT | 24655 | 4215 | 4215 | 4215 | 4215 | 993 | 993 | 97 | 3430 | 3430 | 896 | 3834 | 3834 | 4920 | 8257 | 8257 | 5913 | 12472 | 12472 | 10128
Strl Fabrication (Site) | MT | 29525 |  |  |  |  | 443 | 443 | 442 | 689 | 689 | 750 | 1730 | 1730 | 1149 | 2862 | 2862 | 2341 | 2862 | 2862 | 2341
Strl Erection | MT | 44373 |  |  |  |  | 0 | 0 |  | 175 | 175 | 0 | 826 | 826 | 611 | 1001 | 1001 | 611 | 1001 | 1001 | 611
Equipment Erection | MT | 10503 |  | For the Quarter-Q2 BUD: 0; For the Quarter-Q2 TAR: 0; For the Quarter-Q2 EXP: 0; YTD-Q2 BUD: 0; YTD-Q2 TAR: 0; YTD-Q2 EXP: 0
Piping Fabrication | ID |  |  | For the Quarter-Q2 BUD: 0; For the Quarter-Q2 TAR: 0; For the Quarter-Q2 EXP: 0; YTD-Q2 BUD: 0; YTD-Q2 TAR: 0; YTD-Q2 EXP: 0
Piping Erection | IM | 488769 |  | For the Quarter-Q2 BUD: 0; For the Quarter-Q2 TAR: 0; For the Quarter-Q2 EXP: 0; YTD-Q2 BUD: 0; YTD-Q2 TAR: 0; YTD-Q2 EXP: 0
Electrical Items |  |  |  | For the Quarter-Q2 BUD: 0; For the Quarter-Q2 TAR: 0; For the Quarter-Q2 EXP: 0; YTD-Q2 BUD: 0; YTD-Q2 TAR: 0; YTD-Q2 EXP: 0
… |  |  |  | For the Quarter-Q2 BUD: 0; For the Quarter-Q2 TAR: 0; For the Quarter-Q2 EXP: 0; YTD-Q2 BUD: 0; YTD-Q2 TAR: 0; YTD-Q2 EXP: 0
SITE SERVICES - Mech & Other Items (Financials)
Invoice | Crs. | 542.8253 |  | 0 | 0 | 0 | 1.4497 | 1.4497 | 0 | 5.9953 | 5.9953 | 1.4057 | 19.4217 | 19.4217 | 17.2943 | 26.8667 | 26.8667 | 18.7 | 26.8667 | 26.8667 | 18.7
Sales | Crs. | 542.8253 |  | 25.01 | 25.01 | 25.01 | 6.6097 | 6.6097 | 1.4087 | 21.5472 | 21.5472 | 20.3529 | 26.0487 | 26.0487 | 31.5058 | 54.2057 | 54.2057 | 53.2674 | 79.2157 | 79.2157 | 78.2774
Cost | Crs. | 528.3871 |  | 25.01 | 25.01 | 25.01 | 6.6097 | 6.6097 | 1.3833 | 21.5472 | 21.5472 | 20.2658 | 26.0487 | 26.0487 | 31.3876 | 54.2057 | 54.2057 | 53.0367 | 79.2157 | 79.2157 | 78.0467
SITE SERVICES - Total (Financials)
Invoice | Crs. | 808.8121 | 0 | 16 | 16 | 16 | 2.4199 | 2.4199 | 0.87187 | 9.686 | 9.686 | 4.8618 | 21.8743 | 21.8743 | 21.2269 | 33.9802 | 33.9802 | 26.9605 | 49.9802 | 49.9802 | 42.9605
Sales | Crs. | 808.8121 | 0 | 25.61 | 25.61 | 25.61 | 7.0774 | 7.0774 | 1.8225 | 23.1223 | 23.1223 | 21.9367 | 27.1237 | 27.1237 | 32.7695 | 57.3234 | 57.3234 | 56.5287 | 82.9334 | 82.9334 | 82.1387
Cost | Crs. | 725.5588 | 0 | 25.61 | 25.61 | 25.61 | 7.0774 | 7.0774 | 1.83 | 23.1223 | 23.1223 | 21.9367 | 27.1237 | 27.1237 | 32.7695 | 57.3234 | 57.3234 | 56.5362 | 82.9334 | 82.9334 | 82.1462

## Q2-Supply
Details of Q2 - Quantities and Financials (Supply) | [12 empty] | (All figures are in INR Crs.)
Particulars | UOM | TOTAL | ACT till FY21 | YTD Q1 |  |  | 2021-07-01 |  |  | 2021-08-01 |  |  | 2021-09-01 |  |  | For the Quarter-Q2 |  |  | YTD-Q2
|  |  |  | BUD | TAR | ACT | BUD | TAR | ACT | BUD | TAR | ACT | BUD | TAR | EXP | BUD | TAR | EXP | BUD | TAR | EXP
SUPPLY - (Quantities)
Fabricated Structure | MT | 15605 |  | For the Quarter-Q2 BUD: 0; For the Quarter-Q2 TAR: 0; For the Quarter-Q2 EXP: 0; YTD-Q2 BUD: 0; YTD-Q2 TAR: 0; YTD-Q2 EXP: 0
Mech. Bought-out | Crs. | 7.3 |  | For the Quarter-Q2 BUD: 0; For the Quarter-Q2 TAR: 0; For the Quarter-Q2 EXP: 0; YTD-Q2 BUD: 0; YTD-Q2 TAR: 0; YTD-Q2 EXP: 0
Elec. Bought-out | Crs. |  |  | For the Quarter-Q2 BUD: 0; For the Quarter-Q2 TAR: 0; For the Quarter-Q2 EXP: 0; YTD-Q2 BUD: 0; YTD-Q2 TAR: 0; YTD-Q2 EXP: 0
Raw Steel (Outside site) | MT |  |  | For the Quarter-Q2 BUD: 0; For the Quarter-Q2 TAR: 0; For the Quarter-Q2 EXP: 0; YTD-Q2 BUD: 0; YTD-Q2 TAR: 0; YTD-Q2 EXP: 0
SUPPLY - (Financials)
Invoice | Crs. | 156 |  | For the Quarter-Q2 BUD: 0; For the Quarter-Q2 TAR: 0; For the Quarter-Q2 EXP: 0; YTD-Q2 BUD: 0; YTD-Q2 TAR: 0; YTD-Q2 EXP: 0
Sales | Crs. | 156 |  | For the Quarter-Q2 BUD: 0; For the Quarter-Q2 TAR: 0; For the Quarter-Q2 EXP: 0; YTD-Q2 BUD: 0; YTD-Q2 TAR: 0; YTD-Q2 EXP: 0
Cost | Crs. | 133.1 |  | For the Quarter-Q2 BUD: 0; For the Quarter-Q2 TAR: 0; For the Quarter-Q2 EXP: 0; YTD-Q2 BUD: 0; YTD-Q2 TAR: 0; YTD-Q2 EXP: 0
SITE SERVICES - Total (Financials)
Invoice | Crs. | 808.8121 | 0 | 16 | 16 | 16 | 2.4199 | 2.4199 | 0.87187 | 9.686 | 9.686 | 4.8618 | 21.8743 | 21.8743 | 21.2269 | 33.9802 | 33.9802 | 26.9605 | 49.9802 | 49.9802 | 42.9605
Sales | Crs. | 808.8121 | 0 | 25.61 | 25.61 | 25.61 | 7.0774 | 7.0774 | 1.8225 | 23.1223 | 23.1223 | 21.9367 | 27.1237 | 27.1237 | 32.7695 | 57.3234 | 57.3234 | 56.5287 | 82.9334 | 82.9334 | 82.1387
Cost | Crs. | 725.5588 | 0 | 25.61 | 25.61 | 25.61 | 7.0774 | 7.0774 | 1.83 | 23.1223 | 23.1223 | 21.9367 | 27.1237 | 27.1237 | 32.7695 | 57.3234 | 57.3234 | 56.5362 | 82.9334 | 82.9334 | 82.1462
TOTAL
Invoice | Crs. | 964.8121 | 0 | 16 | 16 | 16 | 2.4199 | 2.4199 | 0.87187 | 9.686 | 9.686 | 4.8618 | 21.8743 | 21.8743 | 21.2269 | 33.9802 | 33.9802 | 26.9605 | 49.9802 | 49.9802 | 42.9605
Sales | Crs. | 964.8121 | 0 | 25.61 | 25.61 | 25.61 | 7.0774 | 7.0774 | 1.8225 | 23.1223 | 23.1223 | 21.9367 | 27.1237 | 27.1237 | 32.7695 | 57.3234 | 57.3234 | 56.5287 | 82.9334 | 82.9334 | 82.1387
Cost | Crs. | 858.6588 | 0 | 25.61 | 25.61 | 25.61 | 7.0774 | 7.0774 | 1.83 | 23.1223 | 23.1223 | 21.9367 | 27.1237 | 27.1237 | 32.7695 | 57.3234 | 57.3234 | 56.5362 | 82.9334 | 82.9334 | 82.1462
GM | Crs. | 106.1532 | 0 | 0 | 0 | 0 | 0 | 0 | -0.007477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.007477 | 0 | 0 | -0.007477
GM% | % | 11%

## Q3-Site Services
Details of Q3 - Quantities and Financials (Site Services) | [12 empty] | (All figures are in INR Crs.)
Particulars | UOM | TOTAL | ACT till FY21 | YTD Q2 |  |  | 2021-10-01 |  |  | 2021-11-01 |  |  | 2021-12-01 |  |  | For the Quarter-Q3 |  |  | YTD-Q3
|  |  |  | BUD | TAR | EXP | BUD | TAR | EXP | BUD | TAR | EXP | BUD | TAR | EXP | BUD | TAR | EXP | BUD | TAR | EXP
SITE SERVICES - CIVIL (Quantities)
Excavation | Cum | 305000 | 0 | 0 | 0 | 21650 | 16752.7682 | 16752.7682 | 16752.7682 | 20702.6886 | 20702.6886 | 34504.481 | 26000.357 | 26000.357 | 37681.6768 | 63455.8138 | 63455.8138 | 88938.926 | 63455.8138 | 63455.8138 | 110588.926
Concrete | Cum | 132500 | 0 | 18180 | 18180 | 19014 | 5776.8166 | 5776.8166 | 5776.8166 | 7198.0969 | 7198.0969 | 11898.0969 | 9027.6817 | 9027.6817 | 12993.6817 | 22002.5952 | 22002.5952 | 30668.5952 | 40182.5952 | 40182.5952 | 49682.5952
Shuttering | Sqm | 448500 | 0 | 9090 | 9090 | 9507 | 11553.6332 | 11553.6332 | 5776.8166 | 14396.1938 | 14396.1938 | 23796.1938 | 18055.3633 | 18055.3633 | 19490.5225 | 44005.1903 | 44005.1903 | 49063.5329 | 53095.1903 | 53095.1903 | 58570.5329
Rebar | MT | 12840 | 0 | 1817.8 | 1817.8 | 1902 | 548.7976 | 548.7976 | 578 | 683.8192 | 683.8192 | 1190 | 857.6298 | 857.6298 | 1299 | 2090.2465 | 2090.2465 | 3067 | 3908.0465 | 3908.0465 | 4969
… |  | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
SITE SERVICES - CIVIL (Financials)
Invoice | Crs. | 265.9868 | 0 | 23.1135 | 23.1135 | 24.2605 | 3.8352 | 3.8352 | 3.4718 | 4.7728 | 4.7728 | 8.558 | 5.9871 | 5.9871 | 9.4695 | 14.5951 | 14.5951 | 21.4993 | 37.7086 | 37.7086 | 45.7598
Sales | Crs. | 265.9868 | 0 | 3.7177 | 3.7177 | 3.8613 | 1.6655 | 1.6655 | 1.6243 | 2.0752 | 2.0752 | 4.3062 | 2.6027 | 2.6027 | 4.1784 | 6.3433 | 6.3433 | 10.1089 | 10.0611 | 10.0611 | 13.9702
Cost | Crs. | 197.1717 | 0 | 3.7177 | 3.7177 | 4.0994 | 1.8497 | 1.8497 | 1.6243 | 2.3029 | 2.3029 | 4.3062 | 2.8887 | 2.8887 | 4.1784 | 7.0414 | 7.0414 | 10.1089 | 10.7591 | 10.7591 | 14.2083
SITE SERVICES - Mech & Other Items (Quantities)
Raw Steel (Site) | MT | 24655 | 4215 | 12472 | 12472 | 10128 | 2000 | 2000 | 831 | 2000 | 2000 | 4314 | 2500 | 2500 | 2500 | 6500 | 6500 | 7645 | 18972 | 18972 | 17773
Strl Fabrication (Site) | MT | 29525 | 0 | 2862 | 2862 | 2341 | 1714 | 1714 | 1564 | 2114 | 2114 | 2264 | 2152 | 2152 | 2897 | 5980 | 5980 | 6725 | 8842 | 8842 | 9066
Strl Erection | MT | 44373 | 0 | 1001 | 1001 | 611 | 725 | 725 | 943 | 1295 | 1295 | 1865 | 1825 | 1825 | 2125 | 3845 | 3845 | 4933 | 4846 | 4846 | 5544
Equipment Erection | MT | 10503 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Piping Fabrication | ID | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Piping Erection | IM | 488769 | 0 | 0 | 0 | 0 | [6 empty] | 2398 | 2398 | 2399.9983 | 2398 | 2398 | 2399.9983 | 2398 | 2398 | 2399.9983
Electrical Items |  | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
… |  | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
SITE SERVICES - Mech & Other Items (Financials)
Invoice | Crs. | 542.8253 | 0 | 26.8667 | 26.8667 | 18.7 | 18.8358 | 18.8358 | 9.5847 | 25.1754 | 25.1754 | 30.793 | 26.7145 | 30.4685 | 35.1729 | 70.7257 | 74.4797 | 75.5506 | 97.5924 | 101.3464 | 94.2507
Sales | Crs. | 542.8253 | 0 | 79.2157 | 79.2157 | 78.2774 | 16.8345 | 16.8345 | 8.7798 | 17.8248 | 17.8248 | 35.4693 | 22.2473 | 22.2473 | 25.3779 | 56.9067 | 56.9067 | 69.627 | 136.1223 | 136.1223 | 147.9044
Cost | Crs. | 528.3871 | 0 | 79.2157 | 79.2157 | 78.0467 | 16.4266 | 16.4266 | 9.1671 | 17.4169 | 17.4169 | 35.4693 | 21.8394 | 21.8394 | 25.3779 | 55.6829 | 55.6829 | 70.0142 | 134.8986 | 134.8986 | 148.061
SITE SERVICES - Total (Financials)
Invoice | Crs. | 808.8121 | 0 | 49.9802 | 49.9802 | 42.9605 | 22.671 | 22.671 | 13.0565 | 29.9482 | 29.9482 | 39.351 | 32.7016 | 36.4556 | 44.6424 | 85.3208 | 89.0748 | 97.0499 | 135.301 | 139.055 | 140.0104
Sales | Crs. | 808.8121 | 0 | 82.9334 | 82.9334 | 82.1387 | 18.5 | 18.5 | 10.4041 | 19.9 | 19.9 | 39.7755 | 24.85 | 24.85 | 29.5562 | 63.25 | 63.25 | 79.7358 | 146.1834 | 146.1834 | 161.8745
Cost | Crs. | 725.5588 | 0 | 82.9334 | 82.9334 | 82.1462 | 18.2764 | 18.2764 | 10.7914 | 19.7198 | 19.7198 | 39.7755 | 24.7281 | 24.7281 | 29.5562 | 62.7243 | 62.7243 | 80.1231 | 145.6577 | 145.6577 | 162.2693

## Q3-Supply
Details of Q3 - Quantities and Financials (Supply) | [12 empty] | (All figures are in INR Crs.)
Particulars | UOM | TOTAL | ACT till FY21 | YTD Q2 |  |  | 2021-10-01 |  |  | 2021-11-01 |  |  | 2021-12-01 |  |  | For the Quarter-Q3 |  |  | YTD-Q3
|  |  |  | BUD | TAR | EXP | BUD | TAR | EXP | BUD | TAR | EXP | BUD | TAR | EXP | BUD | TAR | EXP | BUD | TAR | EXP
SUPPLY - (Quantities)
Fabricated Structure | MT | 15605 | 0 | 0 | 0 | 0 | 500 | 500 | 500 | 900 | 900 | 900 | 1500 | 1100 | 1100 | 2900 | 2500 | 2500 | 2900 | 2500 | 2500
Mech. Bought-out | Crs. | 7.3 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Elec. Bought-out | Crs. | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Raw Steel (Outside site) | MT | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
SUPPLY - (Financials)
Invoice | Crs. | 156 | 0 | 0 | 0 | 0 | 4.6925 | 4.6925 | 4.5925 | 8.4465 | 8.4465 | 8.2665 | 14.0775 | 10.3235 | 10.1035 | 27.2165 | 23.4625 | 22.9625 | 27.2165 | 23.4625 | 22.9625
Sales | Crs. | 156 | 0 | 0 | 0 | 0 | 4.52 | 4.52 | 4.25 | 8.48 | 8.48 | 7.65 | 13.12 | 13.12 | 9.35 | 26.12 | 26.12 | 21.25 | 26.12 | 26.12 | 21.25
Cost | Crs. | 133.1 | 0 | 0 | 0 | 0 | 4.52 | 4.52 | 4.25 | 8.48 | 8.48 | 7.65 | 13.12 | 13.12 | 9.35 | 26.12 | 26.12 | 21.25 | 26.12 | 26.12 | 21.25
SITE SERVICES - Total (Financials)
Invoice | Crs. | 808.8121 | 0 | 49.9802 | 49.9802 | 42.9605 | 22.671 | 22.671 | 13.0565 | 29.9482 | 29.9482 | 39.351 | 32.7016 | 36.4556 | 44.6424 | 85.3208 | 89.0748 | 97.0499 | 135.301 | 139.055 | 140.0104
Sales | Crs. | 808.8121 | 0 | 82.9334 | 82.9334 | 82.1387 | 18.5 | 18.5 | 10.4041 | 19.9 | 19.9 | 39.7755 | 24.85 | 24.85 | 29.5562 | 63.25 | 63.25 | 79.7358 | 146.1834 | 146.1834 | 161.8745
Cost | Crs. | 725.5588 | 0 | 82.9334 | 82.9334 | 82.1462 | 18.2764 | 18.2764 | 10.7914 | 19.7198 | 19.7198 | 39.7755 | 24.7281 | 24.7281 | 29.5562 | 62.7243 | 62.7243 | 80.1231 | 145.6577 | 145.6577 | 162.2693
TOTAL
Invoice | Crs. | 964.8121 | 0 | 49.9802 | 49.9802 | 42.9605 | 27.3635 | 27.3635 | 17.649 | 38.3947 | 38.3947 | 47.6175 | 46.7791 | 46.7791 | 54.7459 | 112.5373 | 112.5373 | 120.0124 | 162.5175 | 162.5175 | 162.9729
Sales | Crs. | 964.8121 | 0 | 82.9334 | 82.9334 | 82.1387 | 23.02 | 23.02 | 14.6541 | 28.38 | 28.38 | 47.4255 | 37.97 | 37.97 | 38.9062 | 89.37 | 89.37 | 100.9858 | 172.3034 | 172.3034 | 183.1245
Cost | Crs. | 858.6588 | 0 | 82.9334 | 82.9334 | 82.1462 | 22.7964 | 22.7964 | 15.0414 | 28.1998 | 28.1998 | 47.4255 | 37.8481 | 37.8481 | 38.9062 | 88.8443 | 88.8443 | 101.3731 | 171.7777 | 171.7777 | 183.5193
GM | Crs. | 106.1532 | 0 | 0 | 0 | -0.007477 | 0.22363 | 0.22363 | -0.38726 | 0.18018 | 0.18018 | 0 | 0.1219 | 0.1219 | 0 | 0.52571 | 0.52571 | -0.38726 | 0.52571 | 0.52571 | -0.39474
GM% | % | 11%

## Q4-Site Services
Details of Q4 - Quantities and Financials (Site Services) | [12 empty] | (All figures are in INR Crs.)
Particulars | UOM | TOTAL | ACT till FY21 | YTD Q3 |  |  | 2022-01-01 |  |  | 2022-02-01 |  |  | 2022-03-01 |  |  | For the Quarter-Q4 |  |  | YTD-Q4
|  |  |  | BUD | TAR | EXP | BUD | TAR | EXP | BUD | TAR | EXP | BUD | TAR | EXP | BUD | TAR | EXP | BUD | TAR | EXP
SITE SERVICES - CIVIL (Quantities)
Excavation | Cum | 305000 | 0 | 63455.8138 | 63455.8138 | 110588.926 | 29355.3955 | 29355.3955 | 44477.872 | 29630.0115 | 29630.0115 | 44893.9567 | 29161.8431 | 29161.8431 | 44184.6107 | 88147.25 | 88147.25 | 133556.4394 | 151603.0638 | 151603.0638 | 244145.3654
Concrete | Cum | 132500 | 0 | 40182.5952 | 40182.5952 | 49682.5952 | 10137.1972 | 10137.1972 | 15337.1972 | 10280.6747 | 10280.6747 | 15480.6747 | 10036.0727 | 10036.0727 | 15236.0727 | 30453.9446 | 30453.9446 | 46053.9446 | 70636.5398 | 70636.5398 | 95736.5398
Shuttering | Sqm | 448500 | 0 | 53095.1903 | 53095.1903 | 58570.5329 | 20274.3945 | 20274.3945 | 46011.5917 | 20561.3495 | 20561.3495 | 54182.3616 | 20072.1453 | 20072.1453 | 53326.2543 | 60907.8893 | 60907.8893 | 153520.2076 | 114003.0796 | 114003.0796 | 212090.7405
Rebar | MT | 12840 | 0 | 3908.0465 | 3908.0465 | 4969 | 963.0337 | 963.0337 | 1534 | 976.6641 | 976.6641 | 1548 | 953.4269 | 953.4269 | 1524 | 2893.1247 | 2893.1247 | 4606 | 6801.1713 | 6801.1713 | 9575
… |  | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
SITE SERVICES - CIVIL (Financials)
Invoice | Crs. | 265.9868 | 0 | 37.7086 | 37.7086 | 45.7598 | 6.7286 | 6.7286 | 12.9412 | 6.8189 | 6.8189 | 13.973 | 6.6649 | 6.6649 | 15.307 | 20.2123 | 20.2123 | 42.2213 | 57.921 | 57.921 | 87.981
Sales | Crs. | 265.9868 | 0 | 10.0611 | 10.0611 | 13.9702 | 2.9226 | 2.9226 | 12.9412 | 2.9639 | 2.9639 | 13.973 | 2.8934 | 2.8934 | 15.307 | 8.7799 | 8.7799 | 42.2213 | 18.841 | 18.841 | 56.1914
Cost | Crs. | 197.1717 | 0 | 10.7591 | 10.7591 | 14.2083 | 3.2455 | 3.2455 | 7.2217 | 3.2898 | 3.2898 | 8.1316 | 3.2142 | 3.2142 | 8.1746 | 9.7495 | 9.7495 | 23.5278 | 20.5086 | 20.5086 | 37.7362
SITE SERVICES - Mech & Other Items (Quantities)
Raw Steel (Site) | MT | 24655 | 4215 | 18972 | 18972 | 17773 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 1683 | 1683 | 3142 | 5683 | 5683 | 7142 | 24655 | 24655 | 24915
Strl Fabrication (Site) | MT | 29525 | 0 | 8842 | 8842 | 9066 | 2445 | 2445 | 2895 | 2784 | 2784 | 3526 | 2477 | 2477 | 3727 | 7706 | 7706 | 10148 | 16548 | 16548 | 19214
Strl Erection | MT | 44373 | 0 | 4846 | 4846 | 5544 | 2358 | 2358 | 2713 | 2655 | 2655 | 4310 | 2900 | 2900 | 4725 | 7913 | 7913 | 11748 | 12759 | 12759 | 17292
Equipment Erection | MT | 10503 | 0 | 0 | 0 | 0 |  |  | 250 |  |  | 500 | 70 | 70 | 1250 | 70 | 70 | 2000 | 70 | 70 | 2000
Piping Fabrication | ID | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Piping Erection | IM | 488769 | 0 | 2398 | 2398 | 2399.9983 | 2997.543 | 2997.543 | 8000 | 2997.543 | 2997.543 | 12000 | 7993.448 | 7993.448 | 17600 | 13988.534 | 13988.534 | 37600 | 16386.534 | 16386.534 | 39999.9983
Electrical Items |  | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
… |  | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
SITE SERVICES - Mech & Other Items (Financials)
Invoice | Crs. | 542.8253 | 0 | 97.5924 | 101.3464 | 94.2507 | 37.0035 | 43.1976 | 27.9131 | 38.8477 | 36.9707 | 55.4487 | 47.3062 | 43.5522 | 56.6477 | 123.1574 | 123.7205 | 140.0094 | 220.7498 | 225.0669 | 234.2601
Sales | Crs. | 542.8253 | 0 | 136.1223 | 136.1223 | 147.9044 | 27.5614 | 27.5614 | 24.1056 | 29.0406 | 29.0406 | 28.6228 | 27.4822 | 27.4822 | 44.5519 | 84.0842 | 84.0842 | 97.2803 | 220.2065 | 220.2065 | 245.1847
Cost | Crs. | 528.3871 | 0 | 134.8986 | 134.8986 | 148.061 | 19.6067 | 19.6067 | 21.1056 | 21.086 | 21.086 | 25.6228 | 19.5275 | 19.5275 | 35.5519 | 60.2202 | 60.2202 | 82.2803 | 195.1188 | 195.1188 | 230.3413
SITE SERVICES - Total (Financials)
Invoice | Crs. | 808.8121 | 0 | 135.301 | 139.055 | 140.0104 | 43.7321 | 49.9262 | 40.8543 | 45.6666 | 43.7896 | 69.4218 | 53.9711 | 50.2171 | 71.9547 | 143.3697 | 143.9328 | 182.2307 | 278.6707 | 282.9878 | 322.2411
Sales | Crs. | 808.8121 | 0 | 146.1834 | 146.1834 | 161.8745 | 30.4839 | 30.4839 | 37.0468 | 32.0045 | 32.0045 | 42.5958 | 30.3756 | 30.3756 | 59.859 | 92.864 | 92.864 | 139.5016 | 239.0474 | 239.0474 | 301.3761
Cost | Crs. | 725.5588 | 0 | 145.6577 | 145.6577 | 162.2693 | 22.8522 | 22.8522 | 28.3273 | 24.3758 | 24.3758 | 33.7544 | 22.7417 | 22.7417 | 43.7265 | 69.9697 | 69.9697 | 105.8082 | 215.6274 | 215.6274 | 268.0774

## Q4-Supply
Details of Q4 - Quantities and Financials (Supply) | [12 empty] | (All figures are in INR Crs.)
Particulars | UOM | TOTAL | ACT till FY21 | YTD Q3 |  |  | 2022-01-01 |  |  | 2022-02-01 |  |  | 2022-03-01 |  |  | For the Quarter-Q4 |  |  | YTD-Q4
|  |  |  | BUD | TAR | EXP | BUD | TAR | EXP | BUD | TAR | EXP | BUD | TAR | EXP | BUD | TAR | EXP | BUD | TAR | EXP
SUPPLY - (Quantities)
Fabricated Structure | MT | 15605 | 0 | 2900 | 2500 | 2500 | 2560 | 1900 | 1900 | 2500 | 2700 | 2700 | 2500 | 2900 | 2900 | 7560 | 7500 | 7500 | 10460 | 10000 | 10000
Mech. Bought-out | Crs. | 7.3 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Elec. Bought-out | Crs. | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Raw Steel (Outside site) | MT | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 1683 | 1683 | 3142 | 5683 | 5683 | 7142 | 5683 | 5683 | 7142
SUPPLY - (Financials)
Invoice | Crs. | 156 | 0 | 27.2165 | 23.4625 | 22.9625 | 24.0256 | 17.8315 | 17.4515 | 23.4625 | 25.3395 | 24.7995 | 23.4625 | 27.2165 | 26.6365 | 70.9506 | 70.3875 | 68.8875 | 98.1671 | 93.85 | 91.85
Sales | Crs. | 156 | 0 | 26.12 | 26.12 | 21.25 | 23.3717 | 23.3717 | 16.15 | 23.024 | 23.024 | 22.95 | 22.9991 | 22.9991 | 24.65 | 69.3948 | 69.3948 | 63.75 | 95.5148 | 95.5148 | 85
Cost | Crs. | 133.1 | 0 | 26.12 | 26.12 | 21.25 | 23.3717 | 23.3717 | 16.15 | 23.024 | 23.024 | 22.95 | 22.9991 | 22.9991 | 24.65 | 69.3948 | 69.3948 | 63.75 | 95.5148 | 95.5148 | 85
SITE SERVICES - Total (Financials)
Invoice | Crs. | 808.8121 | 0 | 135.301 | 139.055 | 140.0104 | 43.7321 | 49.9262 | 40.8543 | 45.6666 | 43.7896 | 69.4218 | 53.9711 | 50.2171 | 71.9547 | 143.3697 | 143.9328 | 182.2307 | 278.6707 | 282.9878 | 322.2411
Sales | Crs. | 808.8121 | 0 | 146.1834 | 146.1834 | 161.8745 | 30.4839 | 30.4839 | 37.0468 | 32.0045 | 32.0045 | 42.5958 | 30.3756 | 30.3756 | 59.859 | 92.864 | 92.864 | 139.5016 | 239.0474 | 239.0474 | 301.3761
Cost | Crs. | 725.5588 | 0 | 145.6577 | 145.6577 | 162.2693 | 22.8522 | 22.8522 | 28.3273 | 24.3758 | 24.3758 | 33.7544 | 22.7417 | 22.7417 | 43.7265 | 69.9697 | 69.9697 | 105.8082 | 215.6274 | 215.6274 | 268.0774
TOTAL
Invoice | Crs. | 964.8121 | 0 | 162.5175 | 162.5175 | 162.9729 | 67.7577 | 67.7577 | 58.3058 | 69.1291 | 69.1291 | 94.2213 | 77.4336 | 77.4336 | 98.5912 | 214.3203 | 214.3203 | 251.1182 | 376.8378 | 376.8378 | 414.0911
Sales | Crs. | 964.8121 | 0 | 172.3034 | 172.3034 | 183.1245 | 53.8557 | 53.8557 | 53.1968 | 55.0285 | 55.0285 | 65.5458 | 53.3747 | 53.3747 | 84.509 | 162.2589 | 162.2589 | 203.2516 | 334.5623 | 334.5623 | 386.3761
Cost | Crs. | 858.6588 | 0 | 171.7777 | 171.7777 | 183.5193 | 46.224 | 46.224 | 44.4773 | 47.3998 | 47.3998 | 56.7044 | 45.7408 | 45.7408 | 68.3765 | 139.3646 | 139.3646 | 169.5582 | 311.1423 | 311.1423 | 353.0774
GM | Crs. | 106.1532 | 0 | 0.52571 | 0.52571 | -0.39474 | 7.6317 | 7.6317 | 8.7196 | 7.6287 | 7.6287 | 8.8414 | 7.6339 | 7.6339 | 16.1324 | 22.8943 | 22.8943 | 33.6934 | 23.42 | 23.42 | 33.2987
GM% | % | 11%

## Productivity-Q2
Details of Productivity - Q2 | [16 empty] | (All figures are in INR Crs.)
Particulars | UOM | TOTAL SCOPE | Total No. of Man-hours for the Scope (ACE) | Productivity - for the Project |  | YTD: Q1 |  | 2021-07-01 |  | 2021-08-01 |  | 2021-09-01 |  | For Q2 |  | YTD: Q2
|  |  |  | ACE | Target | TAR | ACT | TAR | ACT | TAR | ACT | TAR | EXP | TAR | EXP | TAR | EXP
|  |  |  | MH/Unit | MH/Unit
Concreting* | CUM | 132500 | 5279581.0201 | 39.8459 | 35.8613 | 36 | 13 | 36 | 95 | 36 | 56 | 35.8613 | 35.8613 | 35.8613 | 73 | 35.8613 | 66
Shuttering | SQM | 448500 | 2876189.4107 | 6.4129 | 5.7716 | 6 |  | 6 | 4 | 6 | 6 | 5.7716 | 5.7716 | 5.7716 | 6 | 5.7716 | 6
Rebar | MT | 12840 | 822966.0301 | 64.0939 | 57.6845 | 58 | 100 | 58 | 40 | 58 | 62 | 57.6845 | 57.6845 | 57.6845 | 45 | 57.6845 | 45
Site Fabrication | MT | 29525 | 3544271.7173 | 120.0431 | 108.0388 | 108 |  | 108 | 70 | 108 | 138 | 108.0388 | 108.0388 | 108.0388 | 91 | 108.0388 | 91
Structural Erection | MT | 44373 | 4820055.4559 | 108.6259 | 97.7633 | 98 |  | 98 |  | 98 |  | 97.7633 | 97.7633 | 97.7633 |  | 97.7633
Equipment Erection | MT | 10503 | 837364 | 79.7262 | 71.7536 | 72 |  | 72 |  | 72 |  | 71.7536 |  | 71.7536 |  | 71.7536
Pipe Fabrication | ID
Pipe Erection | IM | 488769 | 1153494.84 | 2.36 | 2.124 | 2 |  | 2 |  | 2 |  | 2.124 |  | 2.124 |  | 2.124
(*) Total civil labour (Man-hours) deployed divided by total quantity executed (RCC+PCC)

## Productivity-Q3
Details of Productivity - Q3 | [12 empty] | (All figures are in INR Crs.)
Particulars | UOM | TOTAL SCOPE | Total No. of Man-hours for the Scope (ACE) | Productivity - for the Project |  | YTD: Q2 |  | 2021-10-01 |  | 2021-11-01 |  | 2021-12-01 |  | For Q3 |  | YTD: Q3
|  |  |  | ACE | Target | TAR | EXP | TAR | EXP | TAR | EXP | TAR | EXP | TAR | EXP | TAR | EXP
|  |  |  | MH/Unit | MH/Unit
Concreting* | CUM | 132500 | 5279581.0201 | 39.8459 | 35.8613 | 35.8613 | 66 | 35.8613 | 35.8613 | 35.8613 | 35.8613 | 35.8613 | 35.8613 | 35.8613 | 35.8613 | 35.8613 | 35.8613
Shuttering | SQM | 448500 | 2876189.4107 | 6.4129 | 5.7716 | 5.7716 | 6 | 5.7716 | 5.7716 | 5.7716 | 5.7716 | 5.7716 | 5.7716 | 5.7716 | 5.7716 | 5.7716 | 5.7716
Rebar | MT | 12840 | 822966.0301 | 64.0939 | 57.6845 | 57.6845 | 45 | 57.6845 | 57.6845 | 57.6845 | 57.6845 | 57.6845 | 57.6845 | 57.6845 | 57.6845 | 57.6845 | 57.6845
Site Fabrication | MT | 29525 | 3544271.7173 | 120.0431 | 108.0388 | 108.0388 | 91 | 108.0388 | 108.0388 | 108.0388 | 108.0388 | 108.0388 | 108.0388 | 108.0388 | 108.0388 | 108.0388 | 108.0388
Structural Erection | MT | 44373 | 4820055.4559 | 108.6259 | 97.7633 | 97.7633 | 0 | 97.7633 | 97.7633 | 97.7633 | 97.7633 | 97.7633 | 97.7633 | 97.7633 | 97.7633 | 97.7633 | 97.7633
Equipment Erection | MT | 10503 | 837364 | 79.7262 | 71.7536 | 71.7536 | 0 | 71.7536 | 71.7536 | 71.7536 | 71.7536 | 71.7536 | 71.7536 | 71.7536 | 71.7536 | 71.7536 | 71.7536
Pipe Fabrication | ID
Pipe Erection | IM | 488769 | 1153494.84 | 2.36 | 2.124 | 2.124 | 0 | 2.124 | 2.124 | 2.124 | 2.124 | 2.124 | 2.124 | 2.124 | 2.124 | 2.124 | 2.124
(*) Total civil labour (Man-hours) deployed divided by total quantity executed (RCC+PCC)

## Productivity-Q4
Details of Productivity - Q4 | [12 empty] | (All figures are in INR Crs.)
Particulars | UOM | TOTAL SCOPE | Total No. of Man-hours for the Scope (ACE) | Productivity - for the Project |  | YTD: Q4 |  | 2022-01-01 |  | 2022-02-01 |  | 2022-03-01 |  | For Q4 |  | YTD: Q4
|  |  |  | ACE | Target | TAR | EXP | TAR | EXP | TAR | EXP | TAR | EXP | TAR | EXP | TAR | EXP
|  |  |  | MH/Unit | MH/Unit
Concreting* | CUM | 132500 | 5279581.0201 | 39.8459 | 35.8613 | 35.8613 | 35.8613 | 35.8613 | 35.8613 | 35.8613 | 35.8613 | 35.8613 | 35.8613 | 35.8613 | 35.8613 | 35.8613 | 35.8613
Shuttering | SQM | 448500 | 2876189.4107 | 6.4129 | 5.7716 | 5.7716 | 5.7716 | 5.7716 | 5.7716 | 5.7716 | 5.7716 | 5.7716 | 5.7716 | 5.7716 | 5.7716 | 5.7716 | 5.7716
Rebar | MT | 12840 | 822966.0301 | 64.0939 | 57.6845 | 57.6845 | 57.6845 | 57.6845 | 57.6845 | 57.6845 | 57.6845 | 57.6845 | 57.6845 | 57.6845 | 57.6845 | 57.6845 | 57.6845
Site Fabrication | MT | 29525 | 3544271.7173 | 120.0431 | 108.0388 | 108.0388 | 108.0388 | 108.0388 | 108.0388 | 108.0388 | 108.0388 | 108.0388 | 108.0388 | 108.0388 | 108.0388 | 108.0388 | 108.0388
Structural Erection | MT | 44373 | 4820055.4559 | 108.6259 | 97.7633 | 97.7633 | 97.7633 | 97.7633 | 97.7633 | 97.7633 | 97.7633 | 97.7633 | 97.7633 | 97.7633 | 97.7633 | 97.7633 | 97.7633
Equipment Erection | MT | 10503 | 837364 | 79.7262 | 71.7536 | 71.7536 | 71.7536 | 71.7536 | 71.7536 | 71.7536 | 71.7536 | 71.7536 | 71.7536 | 71.7536 | 71.7536 | 71.7536 | 71.7536
Pipe Fabrication | ID |  |  |  |  | 0 | 0
Pipe Erection | IM | 488769 | 1153494.84 | 2.36 | 2.124 | 2.124 | 2.124 | 2.124 |  | 2.124 |  | 2.124 |  | 2.124 |  | 2.124
(*) Total civil labour (Man-hours) deployed divided by total quantity executed (RCC+PCC)

## P&M-Q2
Details of P&M - Q2 | [13 empty] | (All figures are in INR Crs.)
Particulars | UOM | TOTAL SCOPE | P&M Cost (Crs.) |  | P&M Unit Cost |  | YTD: Q1 (Unit Cost) |  | Jul-21 (Unit Cost) |  | Aug-21 (Unit Cost) |  | Sep-21 (Unit Cost) |  | For Q2 (Unit Cost) |  | YTD: Q2 (Unit Cost)
|  |  | ACE | Target | ACE | Target | TAR | ACT | TAR | ACT | TAR | ACT | TAR | EXP | TAR | EXP | TAR | EXP
Concreting | CUM | 132500 | 12.7392 | 12.7392 | 961.4491 | 961.4491 | 961.4491 |  | 961.4491 | 1573.44 | 961.4491 | 81.9948 | 961.4491 | 196.3148 | 961.4491 | 169.0437 | 961.4491 | 169.0437
Site Fabrication | MT | 29525 | 8.7717 | 8.7717 | 2970.9377 | 2970.9377 | 3109.9783 |  | 3109.9783 | 2262.4434 | 3109.9783 | 2281.696 | 3109.9783 | 1489.3577 | 3109.9783 | 1889.1687 | 3109.9783 | 2316.3366
Structural Erection | MT | 44373 | 28.1144 | 28.1144 | 6335.9185 | 6335.9185 | 9571.5014 |  | 9571.5014 |  | 9571.5014 |  | 9571.5014 | 8385.0736 | 9571.5014 | 11756.9885 | 9571.5014 | 11756.9885
Equipment Erection | MT | 10503 | 10.0529 | 10.0529 | 9571.5014 | 9571.5014 | 9571.5014 |  | 9571.5014 |  | 9571.5014 |  | 9571.5014 |  | 9571.5014 |  | 9571.5014
Pipe Erection | IM | 488769 | 2.5786 | 2.5786 | 52.7563 | 52.7563 | 52.7563 |  | 52.7563 |  | 52.7563 |  | 52.7563 |  | 52.7563 |  | 52.7563
TOTAL |  |  | 62.2568 | 62.2568
Total P&M Cost | Crs. | NA | 62.2568 | 62.2568 | NA | NA | 0.2212 | 0.1 | 0.3 | 0.22597 | 0.51377 | 0.42795 | 1.1692 | 0.8281 | 1.983 | 1.482 | 2.2042 | 1.582
Total Site Invoice | Crs. | NA | 808.8121 | 808.8121 | NA | NA | 16 | 16 | 2.4199 | 0.87187 | 9.686 | 4.8618 | 21.8743 | 21.2269 | 33.9802 | 26.9605 | 49.9802 | 42.9605
P&M - % of Site Invoice |  | NA | 7.697% | 7.697% | NA | NA | 1.383% | 0.625% | 12.4% | 25.92% | 5.304% | 8.802% | 5.345% | 3.901% | 5.836% | 5.497% | 4.41% | 3.683%
Total Site Cost | Crs. | NA | 725.5588 | 725.5588 | NA | NA | 25.61 | 25.61 | 7.0774 | 1.83 | 23.1223 | 21.9367 | 27.1237 | 32.7695 | 57.3234 | 56.5362 | 82.9334 | 82.1462
P&M - % of Site Cost |  | NA | 8.581% | 8.581% | NA | NA | 0.8637% | 0.3905% | 4.239% | 12.35% | 2.222% | 1.951% | 4.311% | 2.527% | 3.459% | 2.621% | 2.658% | 1.926%

## P&M-Q3
Details of P&M - Q3 | [14 empty] | (All figures are in INR Crs.)
Particulars | UOM | TOTAL SCOPE | P&M Cost (Crs.) |  | P&M Unit Cost |  | YTD: Q2 (Unit Cost) |  | Oct-21 (Unit Cost) |  | Nov-21 (Unit Cost) |  | Dec-21 (Unit Cost) |  | For Q3 (Unit Cost) |  | YTD: Q3 (Unit Cost)
|  |  | ACE | Target | ACE | Target | TAR | EXP | TAR | EXP | TAR | EXP | TAR | EXP | TAR | EXP | TAR | EXP
Concreting | CUM | 132500 | 12.7392 | 12.7392 | 961.4491 | 961.4491 | 961.4491 | 169.0437 | 961.4491 | 961.4491 | 961.4491 | 961.4491 | 961.4491 | 961.4491 | 961.4491 | 961.4491 | 961.4491 | 961.4491
Site Fabrication | MT | 29525 | 8.7717 | 8.7717 | 2970.9377 | 2970.9377 | 3109.9783 | 2316.3366 | 3109.9783 | 3109.9783 | 3109.9783 | 3109.9783 | 3109.9783 | 3109.9783 | 3109.9783 | 3109.9783 | 3109.9783 | 3109.9783
Structural Erection | MT | 44373 | 28.1144 | 28.1144 | 6335.9185 | 6335.9185 | 9571.5014 | 11756.9885 | 9571.5014 | 9571.5014 | 9571.5014 | 9571.5014 | 9571.5014 | 9571.5014 | 9571.5014 | 9571.5014 | 9571.5014 | 9571.5014
Equipment Erection | MT | 10503 | 10.0529 | 10.0529 | 9571.5014 | 9571.5014 | 9571.5014 | 0 | 9571.5014 | 9571.5014 | 9571.5014 | 9571.5014 | 9571.5014 | 9571.5014 | 9571.5014 | 9571.5014 | 9571.5014 | 9571.5014
Pipe Erection | IM | 488769 | 2.5786 | 2.5786 | 52.7563 | 52.7563 | 52.7563 | 0 | 52.7563 | 52.7563 | 52.7563 | 52.7563 | 52.7563 | 52.7563 | 52.7563 | 52.7563 | 52.7563 | 52.7563
TOTAL |  |  | 62.2568 | 62.2568
Total P&M Cost | Crs. | NA | 62.2568 | 62.2568 | NA | NA | 2.2042 | 1.582 | 1.23 | 0.94153 | 1.55 | 1.2482 | 1.79 | 1.6067 | 4.57 | 3.7964 | 6.7742 | 5.3784
Total Site Invoice | Crs. | NA | 808.8121 | 808.8121 | NA | NA | 49.9802 | 42.9605 | 22.671 | 13.0565 | 29.9482 | 39.351 | 36.4556 | 44.6424 | 89.0748 | 97.0499 | 139.055 | 140.0104
P&M - % of Site Invoice |  | NA | 7.697% | 7.697% | NA | NA | 4.41% | 3.683% | 5.425% | 7.211% | 5.176% | 3.172% | 4.91% | 3.599% | 5.131% | 3.912% | 4.872% | 3.841%
Total Site Cost | Crs. | NA | 725.5588 | 725.5588 | NA | NA | 82.9334 | 82.1462 | 18.2764 | 10.7914 | 19.7198 | 39.7755 | 24.7281 | 29.5562 | 62.7243 | 80.1231 | 145.6577 | 162.2693
P&M - % of Site Cost |  | NA | 8.581% | 8.581% | NA | NA | 2.658% | 1.926% | 6.73% | 8.725% | 7.86% | 3.138% | 7.239% | 5.436% | 7.286% | 4.738% | 4.651% | 3.315%

## P&M-Q4
Details of P&M - Q4 | [12 empty] | (All figures are in INR Crs.)
Particulars | UOM | TOTAL SCOPE | P&M Cost (Crs.) |  | P&M Unit Cost |  | YTD: Q3 (Unit Cost) |  | Jan-22 (Unit Cost) |  | Feb-22 (Unit Cost) |  | Mar-22 (Unit Cost) |  | For Q4 (Unit Cost) |  | YTD: Q4 (Unit Cost)
|  |  | ACE | Target | ACE | Target | TAR | EXP | TAR | EXP | TAR | EXP | TAR | EXP | TAR | EXP | TAR | EXP
Concreting | CUM | 132500 | 12.7392 | 12.7392 | 961.4491 | 961.4491 | 961.4491 | 961.4491 | 961.4491 | 961.4491 | 961.4491 | 961.4491 | 961.4491 | 961.4491 | 961.4491 | 961.4491 | 961.4491 | 961.4491
Site Fabrication | MT | 29525 | 8.7717 | 8.7717 | 2970.9377 | 2970.9377 | 3109.9783 | 3109.9783 | 3109.9783 | 3109.9783 | 3109.9783 | 3109.9783 | 3109.9783 | 3109.9783 | 3109.9783 | 3109.9783 | 3109.9783 | 3109.9783
Structural Erection | MT | 44373 | 28.1144 | 28.1144 | 6335.9185 | 6335.9185 | 9571.5014 | 9571.5014 | 9571.5014 | 9571.5014 | 9571.5014 | 9571.5014 | 9571.5014 | 9571.5014 | 9571.5014 | 9571.5014 | 9571.5014 | 9571.5014
Equipment Erection | MT | 10503 | 10.0529 | 10.0529 | 9571.5014 | 9571.5014 | 9571.5014 | 9571.5014 | 9571.5014 | 9571.5014 | 9571.5014 | 9571.5014 | 9571.5014 | 9571.5014 | 9571.5014 | 9571.5014 | 9571.5014 | 9571.5014
Pipe Erection | IM | 488769 | 2.5786 | 2.5786 | 52.7563 | 52.7563 | 52.7563 | 52.7563 | 52.7563 | 52.7563 | 52.7563 | 52.7563 | 52.7563 | 52.7563 | 52.7563 | 52.7563 | 52.7563 | 52.7563
TOTAL |  |  | 62.2568 | 62.2568
Total P&M Cost | Crs. | NA | 62.2568 | 62.2568 | NA | NA | 6.7742 | 5.3784 | 1.8 | 1.6 | 1.88 | 1.7 | 1.89 | 1.7 | 5.57 | 5 | 12.3442 | 10.3784
Total Site Invoice | Crs. | NA | 808.8121 | 808.8121 | NA | NA | 139.055 | 140.0104 | 49.9262 | 40.8543 | 43.7896 | 69.4218 | 50.2171 | 71.9547 | 143.9328 | 182.2307 | 282.9878 | 322.2411
P&M - % of Site Invoice |  | NA | 7.697% | 7.697% | NA | NA | 4.872% | 3.841% | 3.605% | 3.916% | 4.293% | 2.449% | 3.764% | 2.363% | 3.87% | 2.744% | 4.362% | 3.221%
Total Site Cost | Crs. | NA | 725.5588 | 725.5588 | NA | NA | 145.6577 | 162.2693 | 22.8522 | 28.3273 | 24.3758 | 33.7544 | 22.7417 | 43.7265 | 69.9697 | 105.8082 | 215.6274 | 268.0774
P&M - % of Site Cost |  | NA | 8.581% | 8.581% | NA | NA | 4.651% | 3.315% | 7.877% | 5.648% | 7.713% | 5.036% | 8.311% | 3.888% | 7.961% | 4.726% | 5.725% | 3.871%

## Site OH-Q2
Details of Site OH - Q2 | [14 empty] | (All figures are in INR Crs.)
Particulars | UOM | TOTAL SCOPE | Site OH Cost (Crs.) |  | Site OH Unit Cost |  | YTD: Q1 (Unit Cost) |  | Jul-21 (Unit Cost) |  | Aug-21 (Unit Cost) |  | Sep-21 (Unit Cost) |  | For Q2 (Unit Cost) |  | YTD: Q2 (Unit Cost)
|  |  | ACE | Target | ACE | Target | TAR | ACT | TAR | ACT | TAR | ACT | TAR | EXP | TAR | EXP | TAR | EXP
Concreting | CUM | 132500 | 18.2086 | 18.2086 | 1374.2337 | 1374.2337 | 1374.2337 | 1374.2337 | 1374.2337 | 1374.2337 | 1374.2337 | 1374.2337 | 1374.2337 | 1374.2337 | 1374.2337 | 1374.2337 | 1374.2337 | 1374.2337
Site Fabrication | MT | 29525 | 9.2724 | 9.2724 | 3140.5118 | 3140.5118 | 3029.1505 | 3029.1505 | 3029.1505 | 3029.1505 | 3029.1505 | 3029.1505 | 3029.1505 | 3029.1505 | 3029.1505 | 3029.1505 | 3029.1505 | 3029.1505
Structural Erection | MT | 44373 | 20.9155 | 20.9155 | 4713.5586 | 4713.5586 | 4387.7106 | 4387.7106 | 4387.7106 | 4387.7106 | 4387.7106 | 4387.7106 | 4387.7106 | 4387.7106 | 4387.7106 | 4387.7106 | 4387.7106 | 4387.7106
Equipment Erection | MT | 10503 | 16.4066 | 16.4066 | 15620.8778 | 15620.8778 | 14541.0073 | 14541.0073 | 14541.0073 | 14541.0073 | 14541.0073 | 14541.0073 | 14541.0073 | 14541.0073 | 14541.0073 | 14541.0073 | 14541.0073 | 14541.0073
Pipe Erection | IM | 488769 | 2.6201 | 2.6201 | 53.6062 | 53.6062 | 49.9004 | 49.9004 | 49.9004 | 49.9004 | 49.9004 | 49.9004 | 49.9004 | 49.9004 | 49.9004 | 49.9004 | 49.9004 | 49.9004
TOTAL |  |  | 67.4231 | 67.4231
Staff (MM) | MM | NA | 1985 | 1985 | NA | NA | 33 | 33 | 22 | 22 | 36 | 36 | 47 | 47 | 105 | 105 | 138 | 138
Staff Cost | Crs. | NA | 18.5861 | 18.5861 | 27.57% | 27.57% | 0.3069 | 0.3069 | 0.2046 | 0.2046 | 0.3348 | 0.3348 | 0.4371 | 0.4371 | 0.9765 | 0.9765 | 1.2834 | 1.2834
Staff Welfare | Crs. | NA | 2.9999 | 2.9999 | 4.449% | 4.449% | 0.0495 | 0.0495 | 0.033 | 0.033 | 0.054 | 0.054 | 0.0705 | 0.0705 | 0.1575 | 0.1575 | 0.207 | 0.207
RLS (MM) | MM | NA | 1172 | 1172 | NA | NA | 12 | 12 | 18 | 18 | 18 | 18 | 20 | 20 | 56 | 56 | 68 | 68
RLS Cost | Crs. | NA | 5.3079 | 5.3079 | 7.873% | 7.873% | 0.024 | 0.024 | 0.036 | 0.036 | 0.036 | 0.036 | 0.04 | 0.04 | 0.112 | 0.112 | 0.136 | 0.136
Conveyance (Vehicle) |  | NA | 15 | 15 | NA | NA | [8 empty] | 0 | 0 | 0 | 0
Conveyance | Crs. | NA | 5.5096 | 5.5096 | 8.172% | 8.172% | 0.03608 | 0.03608 | 0.0268 | 0.0268 | 0.03648 | 0.03648 | 0.0488 | 0.0488 | 0.11208 | 0.11208 | 0.14816 | 0.14816
Security (Nos.) |  | NA | 18 | 18 | NA | NA | 3 | 3 | 5 | 5 | 5 | 5 | 8 | 8 | 18 | 18 | 21 | 21
Security | Crs. | NA | 1.4516 | 1.4516 | 2.153% | 2.153% | 0.0045 | 0.0045 | 0.0075 | 0.0075 | 0.0075 | 0.0075 | 0.012 | 0.012 | 0.027 | 0.027 | 0.0315 | 0.0315
Others | Crs. | NA | 33.5649 | 33.5649 | 49.78% | 49.78% | 0.23902 | 0.23902 | 0.1321 | 0.1321 | 0.25122 | 0.25122 | 0.3316 | 0.3316 | 0.71492 | 0.71492 | 0.95394 | 0.95394
TOTAL Cost |  |  | 67.42 | 67.42 |  |  | 0.66 | 0.66 | 0.44 | 0.44 | 0.72 | 0.72 | 0.94 | 0.94 | 2.1 | 2.1 | 2.76 | 2.76

## Site OH-Q3
Details of Site OH - Q3 | [14 empty] | (All figures are in INR Crs.)
Particulars | UOM | TOTAL SCOPE | Site OH Cost (Crs.) |  | Site OH Unit Cost |  | YTD: Q2 (Unit Cost) |  | Oct-21 (Unit Cost) |  | Nov-21 (Unit Cost) |  | Dec-21 (Unit Cost) |  | For Q3 (Unit Cost) |  | YTD: Q3 (Unit Cost)
|  |  | ACE | Target | ACE | Target | TAR | EXP | TAR | EXP | TAR | EXP | TAR | EXP | TAR | EXP | TAR | EXP
Concreting | CUM | 132500 | 18.2086 | 18.2086 | 1374.2337 | 1374.2337 | 1374.2337 | 1374.2337 | 1374.2337 | 1374.2337 | 1374.2337 | 1374.2337 | 1374.2337 | 1374.2337 | 1374.2337 | 1374.2337 | 1374.2337 | 1374.2337
Site Fabrication | MT | 29525 | 9.2724 | 9.2724 | 3140.5118 | 3140.5118 | 3029.1505 | 3029.1505 | 3029.1505 | 3029.1505 | 3029.1505 | 3029.1505 | 3029.1505 | 3029.1505 | 3029.1505 | 3029.1505 | 3029.1505 | 3029.1505
Structural Erection | MT | 44373 | 20.9155 | 20.9155 | 4713.5586 | 4713.5586 | 4387.7106 | 4387.7106 | 4387.7106 | 4387.7106 | 4387.7106 | 4387.7106 | 4387.7106 | 4387.7106 | 4387.7106 | 4387.7106 | 4387.7106 | 4387.7106
Equipment Erection | MT | 10503 | 16.4066 | 16.4066 | 15620.8778 | 15620.8778 | 14541.0073 | 14541.0073 | 14541.0073 | 14541.0073 | 14541.0073 | 14541.0073 | 14541.0073 | 14541.0073 | 14541.0073 | 14541.0073 | 14541.0073 | 14541.0073
Pipe Erection | IM | 488769 | 2.6201 | 2.6201 | 53.6062 | 53.6062 | 49.9004 | 49.9004 | 49.9004 | 49.9004 | 49.9004 | 49.9004 | 49.9004 | 49.9004 | 49.9004 | 49.9004 | 49.9004 | 49.9004
TOTAL |  |  | 67.4231 | 67.4231
Staff (MM) | MM | NA | 1985 | 1985 | NA | NA | 138 | 138 | 64 | 64 | 67 | 67 | 70 | 70 | 201 | 201 | 339 | 339
Staff Cost | Crs. | NA | 18.5861 | 18.5861 | 27.57% | 27.57% | 1.2834 | 1.2834 | 0.5952 | 0.5952 | 0.6231 | 0.6231 | 0.651 | 0.651 | 1.8693 | 1.8693 | 3.1527 | 3.1527
Staff Welfare | Crs. | NA | 2.9999 | 2.9999 | 4.449% | 4.449% | 0.207 | 0.207 | 0.096 | 0.096 | 0.1005 | 0.1005 | 0.105 | 0.105 | 0.3015 | 0.3015 | 0.5085 | 0.5085
RLS (MM) | MM | NA | 1172 | 1172 | NA | NA | 68 | 68 | 25 | 25 | 30 | 30 | 30 | 30 | 85 | 85 | 153 | 153
RLS Cost | Crs. | NA | 5.3079 | 5.3079 | 7.873% | 7.873% | 0.136 | 0.136 | 0.05 | 0.05 | 0.06 | 0.06 | 0.06 | 0.06 | 0.17 | 0.17 | 0.306 | 0.306
Conveyance (Vehicle) |  | NA | 15 | 15 | NA | NA | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0
Conveyance | Crs. | NA | 5.5096 | 5.5096 | 8.172% | 8.172% | 0.14816 | 0.14816 | 0.0696 | 0.0696 | 0.0868 | 0.0868 | 0.1 | 0.1 | 0.2564 | 0.2564 | 0.40456 | 0.40456
Security (Nos.) |  | NA | 18 | 18 | NA | NA | 21 | 21 | 10 | 10 | 10 | 10 | 12 | 12 | 32 | 32 | 53 | 53
Security | Crs. | NA | 1.4516 | 1.4516 | 2.153% | 2.153% | 0.0315 | 0.0315 | 0.015 | 0.015 | 0.015 | 0.015 | 0.018 | 0.018 | 0.048 | 0.048 | 0.0795 | 0.0795
Others | Crs. | NA | 33.5649 | 33.5649 | 49.78% | 49.78% | 0.95394 | 0.95394 | 0.4542 | 0.4542 | 0.4546 | 0.4546 | 0.466 | 0.466 | 1.3748 | 1.3748 | 2.3287 | 2.3287
TOTAL Cost |  |  | 67.42 | 67.42 |  |  | 2.76 | 2.76 | 1.28 | 1.28 | 1.34 | 1.34 | 1.4 | 1.4 | 4.02 | 4.02 | 6.78 | 6.78

## Site OH-Q4
Details of Site OH - Q4 | [12 empty] | (All figures are in INR Crs.)
Particulars | UOM | TOTAL SCOPE | Site OH Cost (Crs.) |  | Site OH Unit Cost |  | YTD: Q3 (Unit Cost) |  | Jan-22 (Unit Cost) |  | Feb-22 (Unit Cost) |  | Mar-22 (Unit Cost) |  | For Q4 (Unit Cost) |  | YTD: Q4 (Unit Cost)
|  |  | ACE | Target | ACE | Target | TAR | EXP | TAR | EXP | TAR | EXP | TAR | EXP | TAR | EXP | TAR | EXP
Concreting | CUM | 132500 | 18.2086 | 18.2086 | 1374.2337 | 1374.2337 | 1374.2337 | 1374.2337 | 1374.2337 | 1374.2337 | 1374.2337 | 1374.2337 | 1374.2337 | 1374.2337 | 1374.2337 | 1374.2337 | 1374.2337 | 1374.2337
Site Fabrication | MT | 29525 | 9.2724 | 9.2724 | 3140.5118 | 3140.5118 | 3029.1505 | 3029.1505 | 3029.1505 | 3029.1505 | 3029.1505 | 3029.1505 | 3029.1505 | 3029.1505 | 3029.1505 | 3029.1505 | 3029.1505 | 3029.1505
Structural Erection | MT | 44373 | 20.9155 | 20.9155 | 4713.5586 | 4713.5586 | 4387.7106 | 4387.7106 | 4387.7106 | 4387.7106 | 4387.7106 | 4387.7106 | 4387.7106 | 4387.7106 | 4387.7106 | 4387.7106 | 4387.7106 | 4387.7106
Equipment Erection | MT | 10503 | 16.4066 | 16.4066 | 15620.8778 | 15620.8778 | 14541.0073 | 14541.0073 | 14541.0073 | 14541.0073 | 14541.0073 | 14541.0073 | 14541.0073 | 14541.0073 | 14541.0073 | 14541.0073 | 14541.0073 | 14541.0073
Pipe Erection | IM | 488769 | 2.6201 | 2.6201 | 53.6062 | 53.6062 | 49.9004 | 49.9004 | 49.9004 | 49.9004 | 49.9004 | 49.9004 | 49.9004 | 49.9004 | 49.9004 | 49.9004 | 49.9004 | 49.9004
TOTAL |  |  | 67.4231 | 67.4231
Staff (MM) | MM | NA | 1985 | 1985 | NA | NA | 339 | 339 | 339 | 339 | 79 | 79 | 79 | 79 | 497 | 497 | 836 | 836
Staff Cost | Crs. | NA | 18.5861 | 18.5861 | 27.57% | 27.57% | 3.1527 | 3.1527 | 3.1527 | 3.1527 | 0.7347 | 0.7347 | 0.7347 | 0.7347 | 4.6221 | 4.6221 | 7.7748 | 7.7748
Staff Welfare | Crs. | NA | 2.9999 | 2.9999 | 4.449% | 4.449% | 0.5085 | 0.5085 | 0.5085 | 0.5085 | 0.1185 | 0.1185 | 0.1185 | 0.1185 | 0.7455 | 0.7455 | 1.254 | 1.254
RLS (MM) | MM | NA | 1172 | 1172 | NA | NA | 153 | 153 | 153 | 153 | 35 | 35 | 40 | 40 | 228 | 228 | 381 | 381
RLS Cost | Crs. | NA | 5.3079 | 5.3079 | 7.873% | 7.873% | 0.306 | 0.306 | 0.306 | 0.306 | 0.07 | 0.07 | 0.08 | 0.08 | 0.456 | 0.456 | 0.762 | 0.762
Conveyance (Vehicle) |  | NA | 15 | 15 | NA | NA | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
Conveyance | Crs. | NA | 5.5096 | 5.5096 | 8.172% | 8.172% | 0.40456 | 0.40456 | 0.40456 | 0.40456 | 0.1316 | 0.1316 | 0.1396 | 0.1396 | 0.67576 | 0.67576 | 1.0803 | 1.0803
Security (Nos.) |  | NA | 18 | 18 | NA | NA | 53 | 53 | 53 | 53 | 15 | 15 | 15 | 15 | 83 | 83 | 136 | 136
Security | Crs. | NA | 1.4516 | 1.4516 | 2.153% | 2.153% | 0.0795 | 0.0795 | 0.0795 | 0.0795 | 0.0225 | 0.0225 | 0.0225 | 0.0225 | 0.1245 | 0.1245 | 0.204 | 0.204
Others | Crs. | NA | 33.5649 | 33.5649 | 49.78% | 49.78% | 2.3287 | 2.3287 | 2.3287 | 2.3287 | 0.5027 | 0.5027 | 0.4847 | 0.4847 | 3.3161 | 3.3161 | 5.6449 | 5.6449
TOTAL Cost |  |  | 67.42 | 67.42 |  |  | 6.78 | 6.78 | 6.78 | 6.78 | 1.58 | 1.58 | 1.58 | 1.58 | 9.94 | 9.94 | 16.72 | 16.72